## Sheet1
Peter Kirk PTSA Membership Campaign Timeline
Activities | Month
| August | September | October | November | December | January | February | March | April | May | June
Phase 1: Pre-school year prep
Gain access to MTK, Givebacks, membership alias
Update board roster in Givebacks
Ensure all board members are PTSA members
Obtain list of PK's staff -- full and part-time noted
Review/update membership website messaging
Review/update membership form, post to web
Finalize back-to-school campaign plan
Develop back-to-school campaign materials
Support back-to-school swag bags for families
Finalize dates for membership meetings, meeting format
"Back to Business" email sent to families
Phase 2: Back-to-school campaign
"Back to Business" email sent to families
Print hardcopies of membership form to hand out at events
Membership booth at Eagle Launch/teacher meet and greet
Install QR code yard signs on school campus | bar: Month September
Promote via e-newsletters, social media and principal emails | bar: Month September
Membership booth at back-to-school coffee events | bar: Month September
Membership booth at Back to School Bingo | bar: Month September
Raffle for members at in-person membership meeting | bar: Month September
Phase 3: Fall fundraising campaign
Partner with Director of Fundraising on campaign plan | bar: Month September
Finalize membership messaging for fundraising campaign | bar: Month September
Campaign week -- communications through multiple channels | bar: Month October
Remove membership signs after Fun Run event | bar: Month October
Phase 4: Targeted communications
District public records request for contact info of enrolled families | bar: Month October
Develop targeted communications plan, messaging and distro lists | bar: Month November
Complete targeted communications | bar: Month November
Phase 5: Donated memberships
Offer memberships to families on counselor's list | bar: Month November
Randomly assign donated memberships to staff members | bar: Month November
Randomly assign donated memberships to individuals/families | bar: Month December
Phase 6: Membership awards + wrap up
# of members on Jan. 31 dictates # of annual meeting delegates | bar: Month January
Submit membership award applications | bar: Month February to Month March
Receive awards | bar: Month May
Add award logos to PTSA collateral, web | bar: Month June
Save membership roster for record-keeping | bar: Month June
Send membership roster to treasurer for year-end financial review | bar: Month June
Final dues payments by June 30 | bar: Month June